Contractor Management System

Dependency Analyzer Service Blueprint

Pure Business Logic for Graph Validation, Impact Analysis, and Cascade Processing

Version 1.0 — March 2026

Companion to: CMS Dashboard Cache Architecture v1.0

Companion to: CMS Redis + Celery Blueprint v1.0

Companion to: CMS Database Abstraction Blueprint v1.0

Companion to: CMS Trade Knowledge Templates (separate document)

GOLDEN RULE: The Dependency Analyzer is a pure service. It receives data structures, computes results, returns impact. It never touches the database, never calls ProviderRegistry, never fires Celery tasks, and never makes LLM calls.

# 1. Purpose and Architecture Position

The Dependency Analyzer Service is a pure Python module that performs all graph-related computations for the CMS project dependency system. It operates on two parallel dependency graphs — workgroup-level and job-level — and validates, analyzes, and computes impact for any proposed change.

## 1.1 Three-Layer Position

Per the Dashboard Cache Architecture document (Section 8.6), the CMS uses strict three-layer separation for all business logic:

| Layer | Directory | Rule |
| --- | --- | --- |
| Router | app/routers/ | HTTP handling, immediate write, fire .delay() |
| Worker | app/workers/ | Thin orchestration: get data, call service, save result |
| Service | app/services/ | Pure business logic. No DB. No Celery. Receives data, returns results. |

The Dependency Analyzer lives in the Service layer:

app/services/dependency_analyzer.py    # Main analyzer module

app/services/critical_path.py          # Critical path computation

app/models/dependency.py               # Pydantic models for input/output

## 1.2 What This Service Does

- Validates proposed dependency changes before they are written to the database

- Detects graph violations: cycles, self-references, cross-site links, duplicate edges

- Computes cascading impact: what downstream workgroups and jobs are affected by a change

- Generates human-readable impact summaries for the frontend preview panel

- Identifies orphaned dependencies when a workgroup or job is removed

- Computes the critical path through a project's dependency graph

- Performs topological sort for display ordering (used by dashboard_queries.py)

- Processes batch changes atomically (multiple adds/removes previewed together)

- Reactive analysis: determines what became unblocked when a job completes (used by progress_worker)

- Periodic analysis: computes cascading delays when deadlines are missed (used by deadline_monitor_worker)

- Generates AI insight bullets for the dashboard sidebar based on dependency health

## 1.3 What This Service Does NOT Do

- Never reads from or writes to the database (callers provide data, callers persist results)

- Never imports from app.providers or app.db (zero infrastructure coupling)

- Never fires Celery tasks (the worker that calls this service handles chaining)

- Never makes LLM/Claude API calls (trade knowledge suggestions are a separate service)

- Never raises HTTP exceptions (returns structured error results, callers translate to HTTP)

# 2. Input/Output Contract

The analyzer works with Pydantic models that represent the dependency graph and proposed changes. All data is provided by the caller (router or worker), never fetched internally.

## 2.1 Graph Snapshot (Input)

The caller provides a snapshot of the current dependency graph:

class WorkgroupNode(BaseModel):

id: str

title: str

trade: str

worksite_id: str

status: str

start_date: str | None

end_date: str | None

budget: Decimal

class JobNode(BaseModel):

id: str

title: str

workgroup_id: str

sequence: int

status: str

est_duration_days: int

budget: Decimal

class DependencyEdge(BaseModel):

id: str | None              # None for proposed new edges

from_id: str                 # predecessor (must finish first)

to_id: str                   # dependent (is blocked)

level: Literal['workgroup', 'job']

class ProjectGraph(BaseModel):

workgroups: list[WorkgroupNode]

jobs: list[JobNode]

wg_edges: list[DependencyEdge]

job_edges: list[DependencyEdge]

## 2.2 Proposed Change (Input)

class ChangeOp(BaseModel):

action: Literal[

"add_wg_dep", "remove_wg_dep",

"add_job_dep", "remove_job_dep",

"add_workgroup", "remove_workgroup",

"add_job", "remove_job",

"update_workgroup", "update_job"]

target_id: str | None

from_id: str | None

to_id: str | None

data: dict | None

class BatchChange(BaseModel):

project_id: str

changes: list[ChangeOp]

## 2.3 Validation Result (Output)

class ValidationError(BaseModel):

code: str

message: str

change_index: int

details: dict | None

class ValidationResult(BaseModel):

valid: bool

errors: list[ValidationError]

## 2.4 Impact Analysis Result (Output)

class AffectedEntity(BaseModel):

id: str

title: str

entity_type: Literal['workgroup', 'job']

current_status: str

impact: str

class TimelineShift(BaseModel):

entity_id: str

title: str

entity_type: Literal['workgroup', 'job']

old_earliest_start: str | None

new_earliest_start: str | None

shift_days: int

class OrphanedDep(BaseModel):

edge_id: str

from_title: str

to_title: str

level: Literal['workgroup', 'job']

reason: str

class ImpactResult(BaseModel):

affected_workgroups: list[AffectedEntity]

affected_jobs: list[AffectedEntity]

timeline_shifts: list[TimelineShift]

orphaned_deps: list[OrphanedDep]

newly_unblocked: list[AffectedEntity]

newly_blocked: list[AffectedEntity]

critical_path_before: list[str]

critical_path_after: list[str]

summary: list[str]

class AnalysisResponse(BaseModel):

validation: ValidationResult

impact: ImpactResult | None

graph_after: ProjectGraph | None

## 2.5 Job Completion Result (Output — Reactive Trigger)

When a job completes, the analyzer returns what became unblocked:

class NotificationAction(BaseModel):

recipient_type: Literal['contractor', 'owner', 'contact']

entity_id: str

entity_title: str

message: str

class UnblockedResult(BaseModel):

completed_job: JobNode

completed_workgroup: WorkgroupNode | None

newly_unblocked_jobs: list[JobNode]

newly_unblocked_workgroups: list[WorkgroupNode]

critical_path_changed: bool

critical_path: list[str]

notifications: list[NotificationAction]

## 2.6 Delay Impact Result (Output — Periodic Trigger)

When the deadline monitor runs, the analyzer returns all deadline-related impacts:

class DelayedEntity(BaseModel):

id: str

title: str

entity_type: Literal['workgroup', 'job']

expected_end: str

current_status: str

days_overdue: int

days_until_deadline: int

is_on_critical_path: bool

class CascadingDelay(BaseModel):

source: DelayedEntity

affected: list[AffectedEntity]

estimated_delay_days: int

project_end_impact_days: int

class DeadlineAlert(BaseModel):

entity_id: str

entity_title: str

alert_type: Literal['approaching', 'imminent', 'missed']

days_remaining: int

downstream_count: int

message: str

class DelayImpactResult(BaseModel):

overdue_entities: list[DelayedEntity]

approaching_deadlines: list[DelayedEntity]

cascading_delays: list[CascadingDelay]

alerts: list[DeadlineAlert]

critical_path: list[str]

project_end_at_risk: bool

estimated_project_delay_days: int

ai_insight_bullets: list[str]

# 3. Validation Cases

Every proposed change must pass all applicable validation rules. Rules are checked in priority order — fail fast on the first violation.

## 3.1 Structural Validations

| Rule | Code | Applies To | Error Message |
| --- | --- | --- | --- |
| Self-reference | SELF_REFERENCE | add_wg_dep, add_job_dep | Cannot depend on itself |
| Duplicate edge | DUPLICATE_EDGE | add_wg_dep, add_job_dep | This dependency already exists |
| Entity not found | ENTITY_NOT_FOUND | all operations | Referenced entity does not exist in this project |
| Cross-site WG dep | CROSS_SITE | add_wg_dep | Workgroups on different worksites cannot depend on each other |
| Cross-site job dep | CROSS_SITE_JOB | add_job_dep | Jobs on different worksites cannot depend on each other |

## 3.2 Cycle Detection

A cycle means deadlock — no workgroup in the cycle can ever start. The analyzer uses DFS from the proposed dependent: if it can reach the proposed predecessor through existing forward edges, adding the edge would create a cycle.

def detect_cycle(graph, from_id, to_id, level):

edges = graph.wg_edges if level == 'workgroup' else graph.job_edges

adj = defaultdict(list)

for e in edges:

adj[e.from_id].append(e.to_id)

visited = set()

path = []

def dfs(node):

if node == from_id: return True

if node in visited: return False

visited.add(node); path.append(node)

for neighbor in adj.get(node, []):

if dfs(neighbor): return True

path.pop(); return False

if dfs(to_id):

return [from_id] + path + [from_id]

return None

Error message includes the human-readable cycle path: "Cannot add dependency: Painting → Drywall → Flooring → Painting. This would create a circular dependency."

## 3.3 Status-Based Validations

| Rule | Code | Condition | Message |
| --- | --- | --- | --- |
| Completed predecessor | COMPLETED_PRED_INFO | Predecessor is complete | Warning: predecessor already complete. No scheduling effect. |
| Delete completed job | DELETE_COMPLETED | remove_job, status=complete/paid | Cannot delete a completed or paid job |
| Delete invoiced job | DELETE_INVOICED | remove_job, status=invoiced | Cannot delete a job with pending invoices |
| Remove active WG | REMOVE_ACTIVE_WG | remove_workgroup, status=in_progress | Cannot remove an in-progress workgroup |

## 3.4 Batch Consistency

When processing a batch, later changes must be consistent with earlier ones:

- If change #1 removes a workgroup, change #3 cannot add a dependency to it

- If change #1 adds workgroup A, change #2 can reference A as a dependency target

- If change #1 adds dep A→B and change #2 adds dep B→A, the batch fails (cross-change cycle)

# 4. Impact Analysis Cases

After validation passes, the analyzer computes downstream effects.

## 4.1 Adding a Dependency

### 4.1.1 Predecessor not yet complete

User adds Painting depends on Flooring (in_progress).

- Painting becomes blocked until Flooring completes

- All Painting jobs transitively affected

- Anything depending on Painting is further delayed

- Critical path may extend

### 4.1.2 Predecessor already complete

User adds Flooring depends on Electrical (complete).

- No blocking effect — Flooring can still proceed

- Dependency recorded for documentation/audit

- Summary: "Electrical is already complete. This dependency is satisfied."

### 4.1.3 Multi-predecessor convergence

Drywall depends on Electrical. User adds Drywall depends on HVAC.

- Drywall blocked by whichever predecessor finishes LATER

- If HVAC finishes after Electrical, Drywall's earliest start shifts

- Everything downstream of Drywall shifts accordingly

### 4.1.4 Cross-workgroup job dependency

User adds "Prime all surfaces" depends on "Install LVP flooring".

- Only the specific job is blocked, not the entire workgroup

- Other Painting jobs without this dependency are unaffected

## 4.2 Removing a Dependency

### 4.2.1 Only predecessor removed

Remove Flooring depends on Drywall. Flooring had no other predecessors.

- Flooring becomes unblocked — can start immediately

- Everything downstream may shift earlier

- Critical path may shorten

### 4.2.2 Other predecessors remain

Drywall depends on Electrical AND HVAC. Remove Electrical dependency.

- Drywall still blocked by HVAC

- Timeline only changes if Electrical was the longer path

### 4.2.3 Orphaned job-level deps

Remove WG dep Electrical → Drywall. But job deps exist between their jobs.

- Job-level deps are NOT auto-removed

- Analyzer flags them as potentially orphaned

- Summary: "2 job-level dependencies between Electrical and Drywall still exist. Remove them too?"

- Frontend offers a checkbox: "Also remove related job-level dependencies"

### 4.2.4 Remove job-level dependency

- Only that specific job link is removed

- If WG-level dep still exists, workgroup is still blocked at WG level

- Summary notes which level of blocking remains

## 4.3 Removing a Workgroup

### 4.3.1 Root workgroup (no dependents)

- All jobs cascade-deleted

- All deps where this WG is predecessor are deleted

- No downstream impact

### 4.3.2 Workgroup with dependents

Remove Drywall. Flooring depends on Drywall.

- Flooring loses predecessor — becomes unblocked or blocked by remaining predecessors

- All job-level deps from Drywall jobs are orphaned

- HIGH IMPACT — preview panel must make this very clear

### 4.3.3 Middle of a chain

Chain: Electrical → Drywall → Flooring. Remove Drywall.

- Chain is BROKEN: Electrical and Flooring are no longer connected

- Summary suggests: "Consider adding a direct Electrical → Flooring dependency"

## 4.4 Removing a Job

### 4.4.1 No dependencies

- No graph impact. Just remove the job.

### 4.4.2 Job is a dependency target

- Dependent job loses predecessor

- WG-level dep is unaffected

### 4.4.3 Job has dependents

- Dependents lose predecessor

- Summary flags which job-level links are removed

## 4.5 Adding a Workgroup

- No immediate dependency impact

- If batch includes deps for the new WG, those are validated in context

- Trade Knowledge Templates service (separate doc) can suggest dependencies here

# 5. Critical Path Computation

The critical path is the longest chain through the project. Any delay on it delays the entire project.

## 5.1 Algorithm

Topological-order dynamic programming on the workgroup graph:

def compute_critical_path(graph: ProjectGraph) -> list[str]:

topo = topological_sort(graph)

duration = {wg.id: sum(j.est_duration_days

for j in graph.jobs if j.workgroup_id == wg.id)

for wg in graph.workgroups}

earliest_start = {wg.id: 0 for wg in graph.workgroups}

predecessors = defaultdict(list)

for e in graph.wg_edges:

predecessors[e.to_id].append(e.from_id)

for wg_id in topo:

for pred_id in predecessors.get(wg_id, []):

es = earliest_start[pred_id] + duration[pred_id]

earliest_start[wg_id] = max(earliest_start[wg_id], es)

earliest_finish = {wg_id: earliest_start[wg_id] + duration[wg_id]

for wg_id in earliest_start}

terminal = max(earliest_finish, key=earliest_finish.get)

path = [terminal]

current = terminal

while predecessors.get(current):

pred = max(predecessors[current],

key=lambda p: earliest_finish[p])

path.append(pred)

current = pred

return list(reversed(path))

## 5.2 Timeline Shift Calculation

Re-run forward pass before and after. Compare earliest_start values:

shift_days = new_earliest_start[wg_id] - old_earliest_start[wg_id]

# Positive = delayed, Negative = can start earlier

# 6. Topological Sort

Already implemented in dashboard_queries.py. The analyzer provides a generalized version using Kahn's BFS algorithm:

- Compute in-degree for each node

- Seed queue with roots (in-degree = 0), sorted alphabetically

- Dequeue, add to result, decrement successor in-degrees

- When successor reaches in-degree 0, enqueue (alphabetically)

- If result shorter than node count, cycle exists (safety net)

# 7. Batch Change Processing

The Manage Project UI lets users stage multiple changes. The analyzer processes them atomically.

## 7.1 Processing Order

- Entity additions (add_workgroup, add_job) — create nodes first

- Entity updates (update_workgroup, update_job) — modify existing

- Dependency additions (add_wg_dep, add_job_dep) — add edges

- Dependency removals (remove_wg_dep, remove_job_dep) — remove edges

- Entity removals (remove_job, remove_workgroup) — remove nodes last

## 7.2 Working Copy Pattern

Deep copy the ProjectGraph. Apply changes sequentially, validating each against the working copy:

def analyze_batch(graph, batch):

working = graph.deep_copy()

errors = []

ordered = sort_by_priority(batch.changes)

for i, change in enumerate(ordered):

result = validate_single(working, change)

if not result.valid:

errors.extend(result.errors)

continue

apply_to_working_copy(working, change)

if errors:

return AnalysisResponse(validation=ValidationResult(

valid=False, errors=errors), impact=None, graph_after=None)

impact = compute_impact(graph, working)

return AnalysisResponse(validation=ValidationResult(

valid=True, errors=[]), impact=impact, graph_after=working)

# 8. Integration Points

The analyzer is called from three different contexts, each with different trigger patterns but using the same pure service. The analyzer never knows who is calling it — it receives a ProjectGraph, performs computations, and returns results.

| Trigger | Caller | Analyzer Does | Caller Then Does |
| --- | --- | --- | --- |
| User edits dependency | Router (preview/apply) | Validate + compute impact | Return preview to UI, then persist + cascade |
| Job completes | progress_worker | Compute newly unblocked | Update statuses, notify contractors, unblock next |
| Deadline passes | deadline_monitor_worker | Compute cascading delays | Update critical path, fire alerts, AI insights |

## 8.1 Trigger 1: User Edits Dependency (Synchronous Preview)

When the user clicks "Preview Impact" in the Manage Project UI. This is the primary interactive flow.

### 8.1.1 Preview Endpoint

# app/routers/dependency_changes.py

@router.post('/preview')

async def preview_changes(batch: BatchChange,

providers = Depends(get_providers)):

# 1. Fetch current graph from database

graph = await providers.dashboard.get_project_graph(

batch.project_id)

# 2. Run analyzer (pure logic, no DB calls)

from app.services.dependency_analyzer import analyze_batch

result = analyze_batch(graph, batch)

# 3. Return preview to frontend

if not result.validation.valid:

raise HTTPException(409, detail=result.validation.dict())

return result.impact

### 8.1.2 Apply Endpoint (Async — Pattern 2)

@router.post('/apply')

async def apply_changes(batch: BatchChange,

providers = Depends(get_providers)):

# Re-validate (graph may have changed since preview)

graph = await providers.dashboard.get_project_graph(

batch.project_id)

result = analyze_batch(graph, batch)

if not result.validation.valid:

raise HTTPException(409, detail=result.validation.dict())

# Immediate writes

for change in batch.changes:

await apply_change_to_db(providers, change)

# Fire background cascade

from app.workers.dependency_worker import process_cascade

process_cascade.delay(batch.project_id)

return {'status': 'applied', 'change_count': len(batch.changes)}

### 8.1.3 Cascade Worker (post-apply)

- Recalculate progress percentages (progress_worker chain)

- Refresh dashboard cache (invalidate Redis key)

- Update critical path in project metadata

- Send notifications if workgroups became unblocked

- Publish real-time events for frontend refresh

## 8.2 Trigger 2: Job Completion (Reactive — Event-Driven)

When a job's status changes to 'complete', the progress_worker (already defined in the Celery Blueprint) fires. It needs the analyzer to determine what downstream entities are now unblocked.

### 8.2.1 The Business Problem

In a construction project, completing a job can have cascading effects:

- If a job was the last predecessor for another job, that job can now start

- If all jobs in a workgroup complete, the workgroup itself is complete

- If a workgroup completes, dependent workgroups may become unblocked

- If the completed workgroup was on the critical path, the critical path may shift

- Contractors waiting on this trade need to be notified immediately

### 8.2.2 Analyzer Method: compute_unblocked

The analyzer provides a dedicated method for this event-driven scenario. It takes the current graph plus the ID of the just-completed job, and returns what became unblocked:

class UnblockedResult(BaseModel):

completed_job: JobNode

completed_workgroup: WorkgroupNode | None  # if all jobs done

newly_unblocked_jobs: list[JobNode]

newly_unblocked_workgroups: list[WorkgroupNode]

critical_path_changed: bool

critical_path: list[str]           # updated critical path

notifications: list[NotificationAction]  # who to notify

class NotificationAction(BaseModel):

recipient_type: Literal['contractor', 'owner', 'contact']

entity_id: str

entity_title: str

message: str     # e.g. 'Flooring can now begin. Drywall is complete.'

def compute_unblocked(

graph: ProjectGraph,

completed_job_id: str,

) -> UnblockedResult:

"""

Determine what became unblocked after a job completed.

Pure function — no DB, no notifications sent.

Caller (worker) handles persisting status changes

and dispatching notifications.

"""

...

### 8.2.3 Logic Flow

The compute_unblocked method performs these steps:

- Find the completed job in the graph

- Check all job_edges where this job is a predecessor (from_id = completed_job_id)

- For each dependent job: check if ALL its predecessors are now complete. If yes, it is newly unblocked.

- Check if all jobs in the completed job's workgroup are now complete. If yes, the workgroup itself is complete.

- If the workgroup is complete: check all wg_edges where this workgroup is a predecessor

- For each dependent workgroup: check if ALL its predecessor workgroups are now complete. If yes, it is newly unblocked.

- Recompute the critical path

- Build notification actions for unblocked contractors

### 8.2.4 Worker Integration

The progress_worker calls this method and acts on the result:

# app/workers/progress_worker.py

@app.task(bind=True, max_retries=3)

def recalculate_progress(self, job_id: str):

providers = get_provider_registry()

# 1. Fetch the project graph

job = providers.jobs.get_by_id(job_id)

wg = providers.workgroups.get_by_id(job['workgroup_id'])

ws = providers.worksites.get_by_id(wg['worksite_id'])

graph = providers.dashboard.get_project_graph(ws['project_id'])

# 2. Ask the analyzer what's unblocked (pure logic)

from app.services.dependency_analyzer import compute_unblocked

result = compute_unblocked(graph, job_id)

# 3. Persist status changes

if result.completed_workgroup:

providers.workgroups.update_status(

result.completed_workgroup.id, 'complete')

for wg in result.newly_unblocked_workgroups:

providers.workgroups.update_status(wg.id, 'ready')

# 4. Recalculate progress percentages

#    (workgroup % → worksite % → project %)

recalc_progress_cascade(providers, ws['project_id'])

# 5. Update critical path

if result.critical_path_changed:

providers.projects.update_critical_path(

ws['project_id'], result.critical_path)

# 6. Chain to notification + cache refresh

for action in result.notifications:

send_notification.delay(

action.recipient_type, action.entity_id,

{'message': action.message})

# 7. Invalidate dashboard cache

invalidate_dashboard_cache(ws['project_id'])

Key principle: the worker is thin orchestration. It fetches data, calls the analyzer, persists results, and chains to other workers. The business logic (which jobs are unblocked, which workgroups are complete, what the critical path is) lives entirely in the analyzer.

## 8.3 Trigger 3: Deadline Monitoring (Periodic — Celery Beat)

The deadline_monitor_worker runs every 6 hours (per the Celery Blueprint). It needs the analyzer to compute cascading delay impact when jobs or workgroups miss their deadlines.

### 8.3.1 The Business Problem

When a job or workgroup misses its estimated end date:

- Everything downstream is potentially delayed

- The critical path may now be longer than the project end date

- The business owner needs to know which downstream contractors are affected

- The AI Insights panel should show 'Drywall is 3 days behind. This delays Flooring and Painting by an estimated 3 days.'

- Proactive alerts should fire BEFORE deadlines are missed (3-day, 1-day warnings)

### 8.3.2 Analyzer Method: compute_delay_impact

The analyzer provides a method that takes the current graph plus today's date, and computes all deadline-related impacts:

class DelayedEntity(BaseModel):

id: str

title: str

entity_type: Literal['workgroup', 'job']

expected_end: str          # original estimated end date

current_status: str

days_overdue: int          # 0 if not yet overdue

days_until_deadline: int   # negative if overdue

is_on_critical_path: bool

class CascadingDelay(BaseModel):

source: DelayedEntity                # the overdue entity

affected: list[AffectedEntity]       # downstream entities

estimated_delay_days: int             # propagated delay

project_end_impact_days: int          # how much project end shifts

class DeadlineAlert(BaseModel):

entity_id: str

entity_title: str

alert_type: Literal['approaching', 'imminent', 'missed']

days_remaining: int        # negative if missed

downstream_count: int      # how many entities are affected

message: str               # human-readable for notifications

class DelayImpactResult(BaseModel):

overdue_entities: list[DelayedEntity]

approaching_deadlines: list[DelayedEntity]  # within 7 days

cascading_delays: list[CascadingDelay]

alerts: list[DeadlineAlert]

critical_path: list[str]

project_end_at_risk: bool

estimated_project_delay_days: int

ai_insight_bullets: list[str]  # feed directly to AI Insights panel

def compute_delay_impact(

graph: ProjectGraph,

today: date,

) -> DelayImpactResult:

"""

Analyze all deadline-related impacts across the project.

Pure function — no DB, no notifications sent.

Caller (worker) handles alerts and cache updates.

"""

...

### 8.3.3 Logic Flow

The compute_delay_impact method performs these steps:

- Compute expected end date for each workgroup/job using start_date + cumulative duration (respecting dependency ordering via topological sort)

- Compare expected end dates against today. Flag overdue and approaching entities.

- For each overdue entity: walk the graph forward, computing propagated delay. If Drywall is 3 days late, Flooring's earliest start shifts by 3 days, which shifts Painting by 3 days.

- Check if any cascading delay pushes past the project end date

- Compute the critical path and check if overdue entities are on it (critical path delays are project-level delays; non-critical delays have float/slack)

- Build deadline alerts categorized by severity: approaching (3-7 days), imminent (1-2 days), missed (overdue)

- Generate AI insight bullet points in natural language for the dashboard sidebar

### 8.3.4 Worker Integration

# app/workers/deadline_monitor_worker.py

@app.task

def monitor_deadlines():

providers = get_provider_registry()

today = date.today()

# Iterate all active projects

projects = providers.projects.list_active()

for project in projects:

graph = providers.dashboard.get_project_graph(project['id'])

# Ask the analyzer for delay impact (pure logic)

from app.services.dependency_analyzer import compute_delay_impact

result = compute_delay_impact(graph, today)

# Persist updated critical path

if result.critical_path:

providers.projects.update_critical_path(

project['id'], result.critical_path)

# Fire deadline alerts (deduplicated via Redis set)

for alert in result.alerts:

dedup_key = f'cms:notified:deadline:{alert.entity_id}:{alert.alert_type}'

if not redis_client.exists(dedup_key):

send_notification.delay(

'deadline_' + alert.alert_type,

alert.entity_id,

{'message': alert.message})

redis_client.setex(dedup_key, 86400, '1')  # 24h dedup

# Update AI insights cache

if result.ai_insight_bullets:

cache_key = f'cms:cache:deadline_insights:{project["id"]}'

redis_client.set_json(cache_key, result.ai_insight_bullets, ttl=21600)

## 8.4 Trigger Integration Summary

All three triggers use the same analyzer, the same ProjectGraph input, and the same pure-function pattern. The difference is only in what the caller provides and what it does with the result:

| Aspect | User Edit (8.1) | Job Completion (8.2) | Deadline Monitor (8.3) |
| --- | --- | --- | --- |
| Trigger | User action in UI | Job status → complete | Celery Beat (every 6h) |
| Caller | Router + dependency_worker | progress_worker | deadline_monitor_worker |
| Analyzer method | analyze_batch() | compute_unblocked() | compute_delay_impact() |
| Input (besides graph) | BatchChange (proposed edits) | completed_job_id | today's date |
| Output used for | Preview panel in UI | Status updates + notifications | Alerts + AI insights + critical path |
| DB writes by | Router (apply endpoint) | progress_worker | deadline_monitor_worker |
| Downstream workers | process_cascade → notify | notify + cache refresh | notify (deduplicated) |
| Response pattern | Sync (200/409) | Async (fire-and-forget) | Async (periodic, no response) |

## 8.5 Analyzer API Surface (Complete)

The dependency analyzer exposes exactly three public methods. Each is a pure function with no side effects:

# app/services/dependency_analyzer.py

def analyze_batch(

graph: ProjectGraph,

batch: BatchChange,

) -> AnalysisResponse:

"""Validate proposed changes + compute cascading impact.

Used by: Router (preview/apply endpoints)"""

def compute_unblocked(

graph: ProjectGraph,

completed_job_id: str,

) -> UnblockedResult:

"""Determine what became unblocked after a job completed.

Used by: progress_worker (on job completion event)"""

def compute_delay_impact(

graph: ProjectGraph,

today: date,

) -> DelayImpactResult:

"""Analyze all deadline-related impacts across the project.

Used by: deadline_monitor_worker (every 6 hours)"""

All three methods share internal helpers: topological_sort(), detect_cycle(), compute_critical_path(), compute_earliest_starts(). These are private functions within the module, not exposed to callers.

## 8.6 New Repository Method

# app/db/interfaces/dashboard_repository.py

class IDashboardRepository(ABC):

@abstractmethod

async def get_project_graph(self, project_id: str) -> dict:

"""Return complete dependency graph for a project."""

...

# 9. Error Taxonomy

| Code | Severity | Description |
| --- | --- | --- |
| SELF_REFERENCE | ERROR | Entity cannot depend on itself |
| DUPLICATE_EDGE | ERROR | Dependency already exists |
| ENTITY_NOT_FOUND | ERROR | Referenced entity not in project |
| CROSS_SITE | ERROR | Dependency spans different worksites |
| CYCLE_DETECTED | ERROR | Would create circular dependency |
| DELETE_COMPLETED | ERROR | Cannot delete completed/paid entity |
| DELETE_INVOICED | ERROR | Cannot delete entity with invoices |
| REMOVE_ACTIVE_WG | ERROR | Cannot remove in-progress workgroup |
| BATCH_INCONSISTENCY | ERROR | Later change references entity removed earlier |
| COMPLETED_PRED_INFO | WARNING | Predecessor already complete (no scheduling effect) |
| ORPHANED_JOB_DEPS | WARNING | Job-level deps remain after WG dep removed |
| CHAIN_BROKEN | WARNING | Removing middle node breaks existing chain |

Errors prevent apply. Warnings are included in the impact summary but do not block.

# 10. Testing Strategy

Pure service with no infrastructure dependencies — exhaustive unit tests, no mocks needed.

## 10.1 Test Structure

tests/services/

test_dependency_analyzer.py

test_critical_path.py

conftest.py   # shared graph fixtures

## 10.2 Fixtures

@pytest.fixture

def linear_chain():

"""Electrical -> Drywall -> Flooring -> Painting"""

@pytest.fixture

def diamond_graph():

"""Electrical -> Drywall, HVAC -> Drywall, Drywall -> Painting"""

@pytest.fixture

def multi_site():

"""Two worksites with independent chains"""

## 10.3 Test Cases by Category

| Category | Count | Key Cases |
| --- | --- | --- |
| Cycle detection | 8+ | Simple cycle, indirect, cross-batch, self-reference |
| Cross-site prevention | 4+ | WG cross-site, job cross-site, same-site passes |
| Duplicate detection | 3+ | Exact dup, reverse dup passes, dup across levels |
| Impact: add dep | 6+ | Single pred, multi-pred, already complete, cross-wg job |
| Impact: remove dep | 6+ | Only pred, others remain, orphaned job deps, chain break |
| Impact: remove WG | 5+ | Root, middle, terminal, with jobs, with dependents |
| Impact: remove job | 4+ | No deps, is predecessor, is dependent, last in WG |
| Critical path | 5+ | Linear, diamond, parallel, change shifts path |
| Batch processing | 6+ | Multi-add, add-then-remove, cross-ref new entity |
| Topo sort | 4+ | Linear, diamond, disconnected, cycle safety |

# 11. Implementation Checklist

## 11.1 Files to Create

| File | Purpose |
| --- | --- |
| app/models/dependency.py | Pydantic models: ProjectGraph, ChangeOp, BatchChange, AnalysisResponse |
| app/services/dependency_analyzer.py | Main analyzer: validate, compute impact, analyze_batch |
| app/services/critical_path.py | Critical path algorithm, timeline shift computation |
| app/routers/dependency_changes.py | Preview and apply endpoints |
| tests/services/test_dependency_analyzer.py | Unit tests for all validation and impact cases |
| tests/services/test_critical_path.py | Unit tests for critical path |
| tests/services/conftest.py | Shared graph fixtures |

## 11.2 Files to Modify

| File | Change |
| --- | --- |
| app/db/interfaces/dashboard_repository.py | Add get_project_graph() abstract method |
| app/db/providers/supabase/dashboard_queries.py | Implement get_project_graph() |
| app/routers/__init__.py | Register dependency_changes router |
| app/workers/dependency_worker.py | Add process_cascade task |

## 11.3 Build Order

- Pydantic models (app/models/dependency.py) — define the contract first

- Core graph algorithms (cycle detection, topo sort) — pure functions, easy to test

- Validation engine — all rules from Section 3, with tests

- Impact analysis — all cases from Section 4, with tests

- Critical path computation — Section 5, with tests

- Batch processor — Section 7, with tests

- Repository method (get_project_graph) — Supabase implementation

- Router endpoints (preview + apply) — wire everything together

- Worker integration — cascade processing after apply

Parent Document: CMS Project, Worksite, Workgroup & Job Architecture v5.0

Companion Documents: CMS Dashboard Cache Architecture v1.0, CMS Redis + Celery Blueprint v1.0, CMS Database Abstraction Blueprint v1.0, CMS Trade Knowledge Templates (TBD)

Version: 1.0 — March 2026